## Schedule
HSF Social Communication — 48 Core Post Cycle Tracker ¦ 01 September–27 October 2026
Historical records (01–06 Sep) are preserved as published. From 07 Sep: Mon–Tue Education ¦ Wed–Thu Health ¦ Friday Off ¦ Sat–Sun Climate. Morning overlays remain opportunity-led; P01–P48 headings stay locked.
Calendar # | Date | Day | Week | Programme / Lens | 2-Day Block | Morning Window | Morning ID | Category | Morning Post / Direction | Morning Status | Morning URL | Afternoon Window | Afternoon Stream | Afternoon ID | Issue / Resolution | Afternoon Heading / Post | Format | Afternoon Status | Afternoon URL | Overall Status | Evidence / Safeguarding Check | Notes
1 | 2026-09-01 | Tuesday | Week 1 | E4BL – Education | Historical | 9:00–10:00 AM | FIELD-001 | FIELD | Hazaribagh Center students received learning materials to support classroom activities. | Published |  | 4:00–5:00 PM | Core | P01 | Issue | When Money Becomes a Barrier to Learning | Standard | Published |  | Both Published | Published activity supplied by user; photographs available. Protect children’s privacy; no names, registers or personal details visible. | Historical published record.
2 | 2026-09-02 | Wednesday | Week 1 | E4BL – Education | Historical | 9:00–10:00 AM | MOMENT-001 | MOMENT | Putting the new learning materials to use — students using the materials in ordinary classwork. | Published |  | 4:00–5:00 PM | Core | P02 | Resolution | How Learning Can Continue When Resources Are Limited | Standard | Published |  | Both Published | Use only the observed classroom activity; do not claim improved academic performance from material use. | Historical published record.
3 | 2026-09-03 | Thursday | Week 1 | Mixed – Historical | Historical exception | 9:00–10:00 AM | FIELD-003 | FIELD | Before a medical camp begins — team setup, consultation space and preparation. | Published |  | 4:00–5:00 PM | Overlay | MOMENT-002 | MOMENT | Weekly Cultural / Sports Event — E4BL Uttara Center | Photo / Moment | Published |  | Both Published | Morning: use only verified camp-preparation details and protect patient privacy. Afternoon: weekly E4BL cultural/sports activity was published as an overlay, not a P01–P48 core post. | Pre-new-rhythm historical exception; both posts published.
4 | 2026-09-04 | Friday | Week 1 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
5 | 2026-09-05 | Saturday | Week 1 | A2PHC – Health | Historical | 9:00–10:00 AM | MOMENT-003 | MOMENT | A doctor listening — respectful consultation environment showing human interaction. | Published |  | 4:00–5:00 PM | Core | P13 | Issue | Waiting Too Long Can Make a Manageable Health Concern Harder | Standard | Published |  | Both Published | Describe consultation and respectful interaction only; do not imply diagnosis, successful treatment or recovery. | Historical published record.
6 | 2026-09-06 | Sunday | Week 1 | A2PHC – Health | Historical | 9:00–10:00 AM | FIELD-006 | FIELD | Primary healthcare closer to the community — actual camp location and consultation setting. | Published |  | 4:00–5:00 PM | Core | P14 | Resolution | Primary Care Can Help People Seek the Right Next Step Earlier | Standard | Published |  | Both Published | No patient information, prescriptions, registers or identifiable clinical details in frame. | User confirmed both posts published on 06-Sep-2026.
7 | 2026-09-07 | Monday | Week 1 | E4BL – Education | Block 01 – Day 1 | 9:00–10:00 AM | FIELD-007 | FIELD | Assembly before a regular school day — an authentic E4BL school routine. | Scheduled |  | 4:00–5:00 PM | Core | P03 | Issue | School Dropout Usually Starts Before the Last Day in Class | Standard | Scheduled |  | Scheduled | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Existing scheduled date retained under the revised programme rhythm.
8 | 2026-09-08 | Tuesday | Week 2 | E4BL – Education | Block 01 – Day 2 | 9:00–10:00 AM | OBS-001 | OBS | International Literacy Day — connect literacy with everyday learning and education continuity. | Scheduled |  | 4:00–5:00 PM | Core | P04 | Resolution | Notice the Signs Before Learning Stops | Special Engagement | Scheduled |  | Scheduled | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Existing scheduled date retained under the revised programme rhythm.
9 | 2026-09-09 | Wednesday | Week 2 | A2PHC – Health | Block 02 – Day 1 | 9:00–10:00 AM | FIELD-008 | FIELD | Community health awareness in simple language — use a real A2PHC session or field interaction. | Needs Reschedule |  | 4:00–5:00 PM | Core | P15 | Issue | Health Information Is Everywhere, but Not All of It Is Reliable | Standard | Scheduled |  | Needs Reschedule | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Morning content changed to Health to keep one programme all day; replace the previously scheduled Education morning post. Afternoon core remains scheduled.
10 | 2026-09-10 | Thursday | Week 2 | A2PHC – Health | Block 02 – Day 2 | 9:00–10:00 AM | MOMENT-004 | MOMENT | One health message explained clearly — staff using a poster, flipchart or conversation. | Needs Reschedule |  | 4:00–5:00 PM | Core | P16 | Resolution | Simple Preventive Habits Work Best When the Advice Is Verified | Special Engagement | Scheduled |  | Needs Reschedule | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Morning content changed to Health to keep one programme all day; replace the previously scheduled Education morning post. Afternoon core remains scheduled.
11 | 2026-09-11 | Friday | Week 2 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
12 | 2026-09-12 | Saturday | Week 2 | Climate Action | Block 03 – Day 1 | 9:00–10:00 AM | FIELD-009 | FIELD | Youth climate discussion on heat, changing weather or everyday climate risk. | Planned |  | 4:00–5:00 PM | Core | P23 | Issue | Extreme Heat Is More Than Discomfort | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
13 | 2026-09-13 | Sunday | Week 2 | Climate Action | Block 03 – Day 2 | 9:00–10:00 AM | MOMENT-005 | MOMENT | A practical heat-safety moment — shade, water, rest or safer daily-space choices. | Planned |  | 4:00–5:00 PM | Core | P24 | Resolution | Low-Cost Heat Actions Can Make Daily Spaces Safer | Special Engagement | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
14 | 2026-09-14 | Monday | Week 2 | E4BL – Education | Block 04 – Day 1 | 9:00–10:00 AM | MOMENT-006 | MOMENT | Learning with simple materials — ordinary classwork using what is already available. | Planned |  | 4:00–5:00 PM | Core | P05 | Issue | Learning Should Not Depend on Expensive Materials | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
15 | 2026-09-15 | Tuesday | Week 3 | E4BL – Education | Block 04 – Day 2 | 9:00–10:00 AM | FIELD-010 | FIELD | A regular classroom morning — reading, writing and guided classwork at Hazaribagh or Uttara. | Planned |  | 4:00–5:00 PM | Core | P06 | Resolution | A Simple Learning Routine Can Start With What Is Already Available | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
16 | 2026-09-16 | Wednesday | Week 3 | A2PHC – Health | Block 05 – Day 1 | 9:00–10:00 AM | FIELD-011 | FIELD | Routine primary-care consultation or check environment, if verified and safe to show. | Planned |  | 4:00–5:00 PM | Core | P17 | Issue | Some Health Risks Do Not Announce Themselves Early | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
17 | 2026-09-17 | Thursday | Week 3 | A2PHC – Health | Block 05 – Day 2 | 9:00–10:00 AM | MOMENT-007 | MOMENT | Listening is part of good healthcare — a dignified doctor/community interaction. | Planned |  | 4:00–5:00 PM | Core | P18 | Resolution | Routine Checks Can Support Earlier Professional Attention | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
18 | 2026-09-18 | Friday | Week 3 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
19 | 2026-09-19 | Saturday | Week 3 | Climate Action | Block 06 – Day 1 | 9:00–10:00 AM | FIELD-012 | FIELD | Community discussion on heavy rain, flood risk or locally relevant preparedness. | Planned |  | 4:00–5:00 PM | Core | P25 | Issue | Heavy Rain Becomes More Dangerous When Preparation Starts Too Late | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
20 | 2026-09-20 | Sunday | Week 3 | Climate Action | Block 06 – Day 2 | 9:00–10:00 AM | MOMENT-008 | MOMENT | A household-readiness discussion or practical preparedness moment. | Planned |  | 4:00–5:00 PM | Core | P26 | Resolution | A Simple Household Readiness Plan Can Reduce Avoidable Risk | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
21 | 2026-09-21 | Monday | Week 3 | E4BL – Education | Block 07 – Day 1 | 9:00–10:00 AM | FIELD-013 | FIELD | Guardian–school communication — guardian meeting or teacher-parent discussion. | Planned |  | 4:00–5:00 PM | Core | P07 | Issue | A Child Struggles More When Home and School Work Separately | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
22 | 2026-09-22 | Tuesday | Week 4 | E4BL – Education | Block 07 – Day 2 | 9:00–10:00 AM | MOMENT-009 | MOMENT | One teacher–guardian conversation focused on supporting a learner. | Planned |  | 4:00–5:00 PM | Core | P08 | Resolution | One Small Teacher–Guardian Conversation Can Make Support Clearer | Special Engagement | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
23 | 2026-09-23 | Wednesday | Week 4 | A2PHC – Health | Block 08 – Day 1 | 9:00–10:00 AM | FIELD-014 | FIELD | Community hygiene awareness — safe water, food hygiene, sanitation or handwashing where actually discussed. | Planned |  | 4:00–5:00 PM | Core | P19 | Issue | Small Hygiene Gaps Can Create Bigger Health Risks | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
24 | 2026-09-24 | Thursday | Week 4 | A2PHC – Health | Block 08 – Day 2 | 9:00–10:00 AM | MOMENT-010 | MOMENT | A simple hygiene practice explained or demonstrated in a community setting. | Planned |  | 4:00–5:00 PM | Core | P20 | Resolution | A Household Hygiene Checklist Can Turn Awareness Into Routine | Special Engagement | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
25 | 2026-09-25 | Friday | Week 4 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
26 | 2026-09-26 | Saturday | Week 4 | Climate Action | Block 09 – Day 1 | 9:00–10:00 AM | FIELD-015 | FIELD | Environmental cleanliness or plastic-awareness activity where verified. | Planned |  | 4:00–5:00 PM | Core | P27 | Issue | Single-Use Plastic Leaves a Longer Problem Than Its Short Use | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
27 | 2026-09-27 | Sunday | Week 4 | Climate Action | Block 09 – Day 2 | 9:00–10:00 AM | MOMENT-011 | MOMENT | One practical local environmental action — waste reduction or cleaner surroundings. | Planned |  | 4:00–5:00 PM | Core | P28 | Resolution | Plastic Reduction Works Better as a Practical Habit Than a Slogan | Special Engagement | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
28 | 2026-09-28 | Monday | Week 4 | E4BL – Education | Block 10 – Day 1 | 9:00–10:00 AM | FIELD-016 | FIELD | Regular classroom participation — children staying connected to learning through ordinary school activity. | Planned |  | 4:00–5:00 PM | Core | P09 | Issue | A Small Income Today Can Carry a Long Educational Cost | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
29 | 2026-09-29 | Tuesday | Week 5 | E4BL – Education | Block 10 – Day 2 | 9:00–10:00 AM | MOMENT-012 | MOMENT | Teacher or classroom support that helps children remain engaged with learning. | Planned |  | 4:00–5:00 PM | Core | P10 | Resolution | What Can Help a Child Stay Connected to Learning | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
30 | 2026-09-30 | Wednesday | Week 5 | A2PHC – Health | Block 11 – Day 1 | 9:00–10:00 AM | FIELD-017 | FIELD | Women’s or girls’ health / menstrual-hygiene education only where an approved real session occurs. | Planned |  | 4:00–5:00 PM | Core | P21 | Issue | Shame and Misinformation Can Become Health and Education Barriers | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
31 | 2026-10-01 | Thursday | Week 5 | A2PHC – Health | Block 11 – Day 2 | 9:00–10:00 AM | MOMENT-013 | MOMENT | Practical, private and respectful menstrual-hygiene information in an approved setting. | Planned |  | 4:00–5:00 PM | Core | P22 | Resolution | Menstrual Hygiene Information Should Be Practical, Private and Respectful | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims.
32 | 2026-10-02 | Friday | Week 5 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
33 | 2026-10-03 | Saturday | Week 5 | Climate Action | Block 12 – Day 1 | 9:00–10:00 AM | FIELD-018 | FIELD | Tree care, shade or local environmental conditions as a verified Climate Action activity. | Planned |  | 4:00–5:00 PM | Core | P29 | Issue | Hotter, Harder Spaces Are Often Shaped by the Environment Around Us | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
34 | 2026-10-04 | Sunday | Week 5 | Climate Action | Block 12 – Day 2 | 9:00–10:00 AM | MOMENT-014 | MOMENT | One local resilience choice — shade, tree care, water or community environmental action. | Planned |  | 4:00–5:00 PM | Core | P30 | Resolution | Small Local Design Choices Can Improve Shade, Comfort and Resilience | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity.
35 | 2026-10-05 | Monday | Week 5 | E4BL – Education | Block 13 – Day 1 | 9:00–10:00 AM | OBS-002 | OBS | World Teachers’ Day — recognize HSF teachers through their actual work, not a generic greeting card. | Planned |  | 4:00–5:00 PM | Core | P11 | Issue | Children Need More Than Attendance; They Need Safety and a Voice | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
36 | 2026-10-06 | Tuesday | Week 6 | E4BL – Education | Block 13 – Day 2 | 9:00–10:00 AM | MOMENT-015 | MOMENT | Teacher preparation or a safe classroom moment where children can participate and be heard. | Planned |  | 4:00–5:00 PM | Core | P12 | Resolution | Safe Support Should Make It Easier for a Child to Be Heard | Special Engagement | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes.
37 | 2026-10-07 | Wednesday | Week 6 | A2PHC – Health | Block 14 – Day 1 | 9:00–10:00 AM | FIELD-019 | FIELD | A respectful A2PHC service moment showing access to care without stigma or pity-based framing. | Planned |  | 4:00–5:00 PM | Core | P31 | Issue | Hardship Narrows Choices, but It Should Not Reduce Human Dignity | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
38 | 2026-10-08 | Thursday | Week 6 | A2PHC – Health | Block 14 – Day 2 | 9:00–10:00 AM | MOMENT-016 | MOMENT | Choice and dignity in a consultation or support interaction. | Planned |  | 4:00–5:00 PM | Core | P32 | Resolution | Support Creates More Value When Choice and Respect Remain Visible | Special Engagement | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
39 | 2026-10-09 | Friday | Week 6 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
40 | 2026-10-10 | Saturday | Week 6 | Climate Action | Block 15 – Day 1 | 9:00–10:00 AM | FIELD-020 | FIELD | Youth climate learning as a practical skill — discussion, observation or community action planning. | Planned |  | 4:00–5:00 PM | Core | P33 | Issue | Lack of Money Should Not Mean Lack of a Starting Point | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
41 | 2026-10-11 | Sunday | Week 6 | Climate Action | Block 15 – Day 2 | 9:00–10:00 AM | MOMENT-017 | MOMENT | One climate-learning skill in practice — a participant observing, discussing or proposing an action. | Planned |  | 4:00–5:00 PM | Core | P34 | Resolution | One Useful Skill Can Be Built Through a Small, Structured Learning Path | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
42 | 2026-10-12 | Monday | Week 6 | E4BL – Education | Block 16 – Day 1 | 9:00–10:00 AM | FIELD-021 | FIELD | Safe use of a digital learning resource or guided online learning, where HSF has real evidence. | Planned |  | 4:00–5:00 PM | Core | P35 | Issue | Free Online Learning Helps Only When People Can Find and Use It Safely | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
43 | 2026-10-13 | Tuesday | Week 7 | E4BL – Education | Block 16 – Day 2 | 9:00–10:00 AM | MOMENT-018 | MOMENT | A simple digital-learning routine — guided use of a phone, computer or online learning resource. | Planned |  | 4:00–5:00 PM | Core | P36 | Resolution | A Simple Digital Learning Routine Can Reduce Cost, Confusion and Risk | Special Engagement | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
44 | 2026-10-14 | Wednesday | Week 7 | A2PHC – Health | Block 17 – Day 1 | 9:00–10:00 AM | FIELD-022 | FIELD | Women or girls participating confidently in an approved health-awareness or community discussion. | Planned |  | 4:00–5:00 PM | Core | P37 | Issue | Opportunity Shrinks When Skills, Mobility and Confidence Are Restricted | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
45 | 2026-10-15 | Thursday | Week 7 | A2PHC – Health | Block 17 – Day 2 | 9:00–10:00 AM | OBS-003 | OBS | Global Handwashing Day — connect a real A2PHC hygiene activity to practical prevention. | Planned |  | 4:00–5:00 PM | Core | P38 | Resolution | Skills and Support Can Expand Choice When Agency Remains Central | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
46 | 2026-10-16 | Friday | Week 7 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
47 | 2026-10-17 | Saturday | Week 7 | Climate Action | Block 18 – Day 1 | 9:00–10:00 AM | FIELD-023 | FIELD | Youth climate-justice dialogue — fairness, responsibility and how climate impacts communities. | Planned |  | 4:00–5:00 PM | Core | P39 | Issue | Rights Are Tested in Ordinary Moments, Not Only in Courtrooms | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
48 | 2026-10-18 | Sunday | Week 7 | Climate Action | Block 18 – Day 2 | 9:00–10:00 AM | MOMENT-019 | MOMENT | A participant sharing a perspective on climate fairness, responsibility or community action. | Planned |  | 4:00–5:00 PM | Core | P40 | Resolution | Respect Becomes Real Through Everyday Behaviour | Special Engagement | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
49 | 2026-10-19 | Monday | Week 7 | E4BL – Education | Block 19 – Day 1 | 9:00–10:00 AM | FIELD-024 | FIELD | Inclusive classroom participation — students learning and taking part together. | Planned |  | 4:00–5:00 PM | Core | P41 | Issue | Exclusion Can Be Quiet and Still Cause Harm | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
50 | 2026-10-20 | Tuesday | Week 8 | E4BL – Education | Block 19 – Day 2 | 9:00–10:00 AM | MOMENT-020 | MOMENT | An ordinary classroom moment showing inclusion, respect and participation. | Planned |  | 4:00–5:00 PM | Core | P42 | Resolution | Inclusive Participation Can Be Built Through Small, Repeatable Practices | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
51 | 2026-10-21 | Wednesday | Week 8 | A2PHC – Health | Block 20 – Day 1 | 9:00–10:00 AM | FIELD-025 | FIELD | Health information in practice — staff checking or explaining a verified health message. | Planned |  | 4:00–5:00 PM | Core | P43 | Issue | A Helpful-Looking Post Can Still Be Wrong | Standard | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
52 | 2026-10-22 | Thursday | Week 8 | A2PHC – Health | Block 20 – Day 2 | 9:00–10:00 AM | MOMENT-021 | MOMENT | A simple verification moment before sharing health information with the community. | Planned |  | 4:00–5:00 PM | Core | P44 | Resolution | Pause, Check, Then Share | Special Engagement | Planned |  | Planned | Use current verified A2PHC activity evidence. Protect patient privacy; no prescriptions, registers, diagnoses linked to people or unsupported clinical outcome claims. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
53 | 2026-10-23 | Friday | Week 8 | — | Friday Off | — | — | — | No post | Friday Off |  | — | — | — | — | No post | — | Friday Off |  | Friday Off | No posting on Friday. | Planned weekly pause.
54 | 2026-10-24 | Saturday | Week 8 | Climate Action | Block 21 – Day 1 | 9:00–10:00 AM | FIELD-026 | FIELD | Evidence in climate communication — checking source, context or field information before making a public claim. | Planned |  | 4:00–5:00 PM | Core | P45 | Issue | A Number Without Context Can Mislead | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
55 | 2026-10-25 | Sunday | Week 8 | Climate Action | Block 21 – Day 2 | 9:00–10:00 AM | HSF-001 | HSF | Behind a responsible climate post — staff reviewing scope, period and source before publication. | Planned |  | 4:00–5:00 PM | Core | P46 | Resolution | Responsible Public Claims Should Show Scope, Period and Source | Standard | Planned |  | Planned | Use current verified Climate Action evidence. Do not invent beneficiary totals, programme activities or impact claims; keep statements proportional to documented activity. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
56 | 2026-10-26 | Monday | Week 8 | E4BL – Education | Block 22 – Day 1 | 9:00–10:00 AM | FIELD-027 | FIELD | A volunteer or partner contributing to a useful E4BL activity. | Planned |  | 4:00–5:00 PM | Core | P47 | Issue | Good Intentions Create More Value When They Become Useful Action | Standard | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.
57 | 2026-10-27 | Tuesday | Week 9 | E4BL – Education | Block 22 – Day 2 | 9:00–10:00 AM | HSF-002 | HSF | Cycle reflection through E4BL — people, partnership and responsible action documented during the communication cycle. | Planned |  | 4:00–5:00 PM | Core | P48 | Resolution | From Empathy to Action: One Responsible Contribution Is Enough to Start | Special Engagement | Planned |  | Planned | Use current verified E4BL activity evidence. Protect children’s dignity and privacy; no unnecessary names, registers or personal details. Do not infer learning outcomes. | Cross-cutting core theme; keep the locked heading and express examples through this day’s programme lens.

## Weekly Rhythm
HSF Weekly Social Communication Rhythm
Operational rhythm from 07 September 2026. The programme stays the same for morning and afternoon; each two-day block carries an Issue → Resolution pair.
Day | Programme | Morning Stream | Afternoon Stream | Pair Role | Posting Rule | Purpose
Monday | E4BL – Education | HSF in Action | Core P-post | Issue | Publish if real/safe morning evidence exists | Begin Education pair
Tuesday | E4BL – Education | HSF in Action | Core P-post | Resolution | Same programme all day | Complete Education pair
Wednesday | A2PHC – Health | HSF in Action | Core P-post | Issue | Publish if real/safe morning evidence exists | Begin Health pair
Thursday | A2PHC – Health | HSF in Action | Core P-post | Resolution | Same programme all day | Complete Health pair
Friday | — | NO POST | NO POST | — | Full weekly pause | Audience and production breathing room
Saturday | Climate Action | HSF in Action | Core P-post | Issue | Publish if real/safe morning evidence exists | Begin Climate pair
Sunday | Climate Action | HSF in Action | Core P-post | Resolution | Same programme all day | Complete Climate pair
Operating Rules
1 | Morning overlays are opportunity-led, not quota-led. If there is no genuine, safe and useful activity, the morning post may be skipped.
2 | From 07 September onward, morning and afternoon must use the same programme lens.
3 | P01–P48 IDs and headings remain locked. The schedule changes dates and programme framing, not the approved core content.
4 | P31–P48 are cross-cutting themes; in this tracker they are expressed through the programme scheduled for that day without changing the locked heading.
5 | Exact-date observances are used only when they fit the day’s programme. Otherwise the observance is skipped rather than breaking the rhythm.
6 | Friday is a deliberate no-post day and is recorded in the tracker rather than omitted.
7 | 01–06 September remain historical records. The new rhythm starts 07 September.

## Dashboard
HSF Social Communication Dashboard ¦ As of 06 September 2026
48 locked core posts + morning HSF in Action overlays. Cycle ends 27 October 2026 because Fridays are intentionally off and 03 September carried an overlay-only afternoon.
Core Posts |  | Published Core |  |  | Core Completion |  | Published Posts
48 |  | 4 |  |  | 8.333% |  | 10
Scheduled Core |  | Planned Core |  |  | Published Morning |  | Friday Off
4 |  | 40 |  |  | 5 |  | 8
Core Status |  | Core Coverage by Programme Lens |  |  |  | Tracker Alerts
Status | Count | Programme | Total Core | Published Core |  | Item | Count
Published | 4 | E4BL – Education | 18 | 2 |  | Needs Reschedule | 2
Scheduled | 4 | A2PHC – Health | 16 | 2 |  | Morning Planned | 40
Planned | 40 | Climate Action | 14 | 0 |  | Morning Skipped | 0
Needs Reschedule | 0
Management Notes
• 06 September is corrected to both posts published.
• 09–10 September morning content requires rescheduling from Education to Health; afternoon P15/P16 remains scheduled.
• Morning overlays are planned opportunities, not compulsory quotas. A weak or unsupported morning post should be skipped.
• Dashboard counts update automatically when Morning Status or Afternoon Status is changed in the Schedule sheet.